# AgriChill Advisor

A software-led cold-room advisory for farmer groups: project report for IEEE Smart Village IdeaRun 2026

Status: DRAFT for team discussion, 13 October 2026. Items marked [VERIFY] are assumptions that must be confirmed in the field before you submit. The official deadline on the IdeaRun page is 31 October 2026; the competition's funding amount and judging criteria are not published there.

# 1. Summary in plain words

Farmers in the same area often harvest the same crop in the same week. When too much produce reaches the market at once, prices crash. Fruits and vegetables spoil quickly, so farmers cannot wait; many sell at a loss or throw the produce away. A cold room lets a farmer hold produce for a few days, but small cold rooms run by farmer groups need tools: who is booking space, how long each batch will stay good, when to sell, and how to use electricity (especially solar) efficiently.

AgriChill Advisor is a simple app, in the local language, for a farmer group and its cold room. It handles bookings, watches storage conditions through off-the-shelf sensors, estimates how many good days each batch has left, suggests when to hold or sell using past market prices, and shows the electricity cost per crate. It is advice for people, not an automatic decision-maker.

# 2. A real-world scenario

The farmer below is a fictional composite, invented to explain the problem. The background facts about tomato price crashes are from public reports; the numbers in the story are illustrative, not data.

Murugan, a tomato farmer in Krishnagiri district, Tamil Nadu

Background that is documented: in 2019, farmers in Rayakottai (Krishnagiri district) and Valappadi (Salem district) dumped tomatoes into lakes after prices fell from about Rs 20 to Rs 2 per kg. A union leader blamed many farmers choosing tomato, a short-season crop. A report said rural cold storage was insufficient and that tomatoes have a low shelf life (sources in section 11).

A day WITHOUT the system

Murugan harvests 3 tonnes. The same week, most farmers around him harvest too. The mandi is full and the trader offers a very low price.

A farmer-group cold room exists 20 km away, but Murugan does not know if space is free, what it costs, or how long his tomatoes would last in it.

The cold-room operator takes bookings on paper and phone calls. Some crates are accepted too late, and the operator cannot tell which batches will spoil first.

Murugan sells below his cost, or throws part of the harvest away.

A day WITH the system (what we propose to build)

Murugan sends a message in Tamil to the farmer group's number and books 40 crates for three days. He sees the price per crate.

A temperature and humidity logger in the cold room feeds the app. Each batch gets an estimate of remaining good days, shown as a range, for example 'about 4 to 6 days'.

The app shows past market prices for his crop and tells him, in plain words, how prices moved after similar glut weeks in earlier seasons, with a clear note that this is not a promise.

The operator sees which batches to sell first, how full the room is, and the electricity cost per crate. The app suggests cooling at times when cheaper or solar power is available.

Murugan decides when to sell. Over a season, the group compares spoilage and income with the previous season.

Honest limit: if market prices do not recover, holding produce does not help. The tool must show uncertainty, not false confidence.

# 3. Where and why the problem occurs

## 3.1 Evidence we found

| Fact | Source | How reliable |
| --- | --- | --- |
| Annual harvest and post-harvest losses of major produce were estimated at Rs 92,651 crore (CIPHET study, 2012-13 production at 2014 prices). | Government reply to Parliament | Official, but dated |
| Ministry figures cited for losses: fruits Rs 16,644 crore, vegetables Rs 14,842 crore. | Global Agriculture, citing a 2021 Lok Sabha reply | Official figures via a news site |
| Press reports give a different figure for fruit and vegetables (about 16% lost, Rs 40,811 crore). | IndiaSpend and FreshPlaza | Conflicts with the above. Use the official figures and state the conflict |
| Tomato prices fell from about Rs 20 to Rs 2 per kg and farmers dumped produce in Rayakottai (Krishnagiri) and Valappadi (Salem), 2019. | The News Minute, Krishi Jagran | News reports, 2019. Needs a current check |
| High up-front cost has held back solar cold storage; business-model pilots are recommended. | SELCO Foundation landscape study terms | NGO document |
| Pay-as-you-use cold storage through FPOs is emerging, with Andhra Pradesh and Maharashtra named as early adopters. | Mongabay India, Nov 2025 | News report on an NCCD report |
| Cold storage capacity is unevenly distributed across states. | A BASE/Empa project note found in search; RBI publishes a state-wise table | Not read in full. Pull the RBI table for your state |

## 3.2 Why it happens (causes)

Same-time harvesting and short-season crops create gluts and price crashes.

Fruits and vegetables are perishable, so farmers cannot wait for better prices.

Cold storage is limited in rural areas and unevenly spread across states.

Solar or efficient cold rooms cost a lot up front, so small groups hesitate.

Small operators and farmers lack simple tools for booking, spoilage risk and sell timing. [VERIFY with 5 farmers and 1 operator: this is our hypothesis, not a proven gap.]

## 3.3 Which state or district?

The problem is national, but the evidence differs by place. Documented examples: tomato gluts in Krishnagiri and Salem (Tamil Nadu), and pay-per-use cold storage through FPOs in Andhra Pradesh and Maharashtra. Choose your pilot district by where you can get a partner (a farmer group or cold-room owner), not by headline statistics. We do not yet know your district; please send it so this section can be made specific.

# 4. Who the project is for, and who benefits

| Group | Problem today | What could change | How we would measure it |
| --- | --- | --- | --- |
| Smallholder farmers, especially members of farmer producer organisations (FPOs) | Forced to sell at harvest-time prices; spoilage | Sell later, lose less | Spoilage %, income per quintal vs last season or vs a comparison group |
| FPO or cold-room operator | Empty or badly planned space; unclear costs | Better bookings, a clear price per crate, lower power cost | Room utilisation %, kWh per quintal, revenue per month |
| Self-help group members and small aggregators handling produce | Same price and storage problems | Shared access through the group's agent or phone | Number of users, repeat bookings |
| Local agriculture advisers (for example agricultural university and Krishi Vigyan Kendra staff) [VERIFY] | Advice is general and not tied to a batch | Local data they can use | Feedback from advisers |
| Consumers and local traders (indirect) | Price swings | Possibly steadier supply | Not measured by this project |

Who may not benefit: farmers without phones or far from a cold room, and larger farmers who adopt faster. We should design for inclusion: voice and local-language messages, access through the group's agent, and a price that smaller farmers can afford.

# 5. What we build

| Module | What it does | AI / method | Data needed |
| --- | --- | --- | --- |
| Booking and inventory | Book crates, track batches, show price per crate; Tamil or local language | None needed, plus an optional language assistant | Farmer group's records |
| Spoilage-risk estimate | Estimate remaining good days for each batch, as a range | Simple probabilistic model using crop shelf-life tables and logger readings, updated as data arrives | Logger data; shelf-life tables from agricultural research bodies [VERIFY source]; manual grading of batches |
| Hold-or-sell guidance | Show past price patterns and arrival trends for the crop | Time-series forecasting with honest error ranges | Daily market prices (see note below) |
| Energy view | Show kWh per crate and suggest cooling times | Rule-based plus a solar or tariff forecast | A commercial clip-on energy meter and tariff |

Why simple models: with one season of small data, a deep neural network cannot be validated and cannot be explained to farmers. A transparent probabilistic model with uncertainty ranges is easier to defend.

Market-price data note: the daily mandi price dataset on data.gov.in is generated from the Agmarknet portal, but its page says no API exists and asks users to request one; a historical archive from Ashoka University (CEDA) exists but needs a key. Check access, terms and limits before relying on either.

# 6. How we prove it works

Month 1 baseline: record last season's spoilage, selling prices and cold-room utilisation for the same group.

Pilot for one harvest season. Compare with the baseline and, if possible, with nearby non-users.

Metrics: spoilage %, income per quintal, room utilisation %, kWh per quintal, number of active users, and a short usability survey.

Be honest in the report: one season and one site cannot prove cause and effect. Say what the result does and does not show.

# 7. Plan and budget structure (6 to 12 months)

| Period | Work |
| --- | --- |
| Month 1 | Interviews, partner agreement, baseline |
| Months 2-3 | Build the minimum version; test with the operator |
| Months 4-6 | Pilot through one harvest season; fix problems |
| Months 7-9 | Improve; add a second site or crop if possible |
| Months 10-12 | Results report; release the code and a how-to guide openly |

Budget lines to price with real quotes: temperature and humidity loggers, energy meters, messaging or SMS costs, field travel, cloud hosting, training sessions for farmers, and printing. Past reported grants were about $2,000 to $2,982 (a college report); do not assume more unless the brochure says so.

# 8. Risks and ethics

No partner: the project fails without a farmer group or cold-room owner. Get a signed letter before submitting.

Season mismatch: your crop's harvest may not fit the timeline. Choose a crop with a season in your window, or a year-round chain such as milk.

Farmer data: get consent, collect only what is needed, store it safely, and explain in Tamil how it is used.

Advice liability: label output as guidance with uncertainty, never a guarantee of profit.

Equipment: use ready-made loggers; do not claim hardware design skills you do not have. Consider adding an EEE or ECE teammate (teams of up to 5 are allowed).

# 9. What is verified and what is not

| Verified from sources | Not verified: confirm before submitting |
| --- | --- |
| IdeaRun 2026 theme, team rules, 1000-word limit, 6-12 month duration, 31 October deadline | The ₹10 lakh figure (not on the page), the 2026 funding amount, the judging criteria |
| National loss estimates (official replies); 2019 tomato price crash in Krishnagiri and Salem | That small operators lack booking and spoilage tools in your district |
| Solar cold-storage cost barrier; pay-per-use FPO models in AP and Maharashtra | Whether your region has a suitable cold room and farmer group |
| Mandi price data exists, with API access restrictions | Shelf-life values for your crop, logger costs, and software-only eligibility |

# 10. Next steps before the deadline

Today: email idearun.isvsarc@gmail.com to confirm funding, deadline and whether software-led proposals are eligible. Ask your faculty mentor whether your college has an earlier internal deadline.

Days 1-4: choose a district and crop; find one farmer group or cold-room owner; get a short letter of support.

Days 4-7: interview 5 farmers and the operator; record a baseline.

Days 8-12: write the 1000-word proposal from this report; get quotes for the budget.

Days 13-16: faculty mentor review. Submit by about 28 October, not on the last day.

# 11. Sources

IdeaRun 2026 page: https://isvsymposium.org/idea-run

CIPHET losses estimate, Lok Sabha reply: https://eparlib.nic.in/bitstream/123456789/706362/1/56899.pdf

Fruit and vegetable loss figures: https://www.global-agriculture.com/national-news/scheme-for-integrated-cold-chain-and-value-addition-infrastructure-in-operation/

Conflicting press figure: https://indiaspend.com/indias-agriculture-produce-losses-rs-92000-cr-3-times-more-than-agriculture-budget-71003

Tomato dumping in Krishnagiri and Salem: https://www.thenewsminute.com/article/tn-farmers-dump-tomato-harvests-lakes-after-prices-drop-77230

SELCO Foundation cold storage landscape study: https://selcofoundation.org/?p=5217

Solar cold storage and FPO pay-per-use (Mongabay India): https://india.mongabay.com/2025/11/solar-powered-cold-storage-empowers-smallholder-farmers/

IIM-Indore study report (news): https://www.freepressjournal.in/amp/indore/cold-storage-alone-cant-stop-indias-food-loss-crisis-iim-i-study

State-wise cold storage capacity table (RBI): https://website.rbi.org.in/web/rbi/-/publications/table-103-state-wise-cold-storage-capacity

Mandi price dataset (data.gov.in): https://data.gov.in/resource/current-daily-price-various-commodities-various-markets-mandi

Reported past IdeaRun grant: https://mgmits.ac.in/ec-news-events/participated-and-granted-2-982-in-the-ieee-smart-village-idearun-2024-national-finals

Prepared with AI assistance from public web sources; search results were summaries, and several source pages were not read in full. Check every figure against the original before you submit.